Q3: Program charter

Mira: vision, scope, success criteria, timeline, risks, stakeholders, decisions and rollout

| Program | Mira: AI-Powered Project Intelligence Assistant |
| --- | --- |
| Sponsor | Santosh Rasputra |
| Program owner | Santosh Rasputra, Project Manager |
| Charter date | 18 October 2026 |
| Pilot data | ABCDE Ltd. AI adoption project files (sample) |

Submitted by Santosh Rasputra

# 1. Vision

Every Nexora project manager gets a grounded first draft of a plan, a risk view and a weekly status report in minutes, and spends the saved time on decisions and people. Mira never invents facts: if the data is missing, it says what is missing.

# 2. Scope

| In scope | Out of scope |
| --- | --- |
| Plans, risk assessments, weekly status reports, task counts, blocked and overdue task alerts, milestone lists, stakeholder update emails | Writing to Jira, Trello, email or Slack; sending messages |
| Input by chat, file upload (CSV, TXT) or API call | Live task board connectors; user accounts and roles |
| Five agents on n8n with gpt-4o-mini; Langfuse tracing; baseline tests T1 to T12 | Fine-tuning; document search over large corpora; human approval steps (reviewed in phase 3) |
| Pilot with 10 PMs and TPMs after the capstone | Company-wide rollout |

# 3. Success criteria

| # | Criterion | Target and evidence |
| --- | --- | --- |
| S1 | Baseline tests T1 to T12 | 12 of 12 baseline tests pass on the live model (18 October 2026); T12 passed after guardrail correction and its trace is marked REVIEW (results file). |
| S2 | Groundedness | 0 invented ids, phases, milestones or figures kept in an answer (guardrail log, Langfuse) |
| S3 | Accuracy of computed content | 100% match to the board in weekly spot checks |
| S4 | Time saved | Report preparation from about 2 hours to under 15 minutes of review (pilot survey; baseline is an assumption to measure) |
| S5 | Cost | Below USD 0.002 per request; below USD 1 per user per month |
| S6 | Adoption | 7 of 10 pilot users use Mira weekly for 4 weeks |

# 4. Timeline

| Phase | Dates | Output |
| --- | --- | --- |
| Scope and design | 12 to 18 Oct 2026 (completed) | Scope of Work v0.6, architecture and workflow design |
| Build and offline test | 16 to 18 Oct 2026 (completed) | Workflow, prompts, guardrails, tests, documents |
| Live run and tuning | 18 to 20 Oct 2026 (live run completed 18 Oct) | Live 12-test run and Langfuse trace review; 12/12 passed. Guardrail and prompt findings are recorded in Q2/Q4; T12 trace is REVIEW after correction. |
| Submission | 21 Oct 2026 target; status updated 24 Oct 2026 | GitHub repository and documents. Slide deck remains pending in the current package. |
| Pilot | From 2 Nov 2026, 4 weeks (proposed) | 10 PMs and TPMs; weekly metrics review |
| Review and decision | Week of 30 Nov 2026 (proposed) | Go, change or stop; approval step and data connectors considered |

# 5. Risks

| # | Risk | Rating | Mitigation and owner |
| --- | --- | --- | --- |
| P1 | The model returns invented or wrong content | High | Code-computed facts; validators; REVIEW flag; weekly sample check. Owner: program owner |
| P2 | Project data is incomplete or out of date | High | Sufficiency gate; as-of date shown in every answer. Owner: each PM |
| P3 | Project data leaves Nexora through the model provider | Medium | Use only approved projects; confirm provider terms; no personal data in prompts. Owner: sponsor |
| P4 | Users over-trust the output | Medium | Footer states sources and checks; training note: review before sending. Owner: program owner |
| P5 | Model or price change alters behavior or cost | Medium | Temperature 0; baseline rerun before any model change; cost shown per trace. Owner: program owner |
| P6 | Live run reveals prompt issues late | Medium | 2 days reserved for tuning; scope cut order set (slide deck, update variants, alert depth). Owner: program owner |
| P7 | Low adoption | Low | Pilot with volunteers; weekly feedback. Owner: sponsor |

# 6. Stakeholders

| Stakeholder | Interest | Involvement |
| --- | --- | --- |
| Sponsor, Santosh Rasputra | Productivity and cost | Approves scope, pilot and rollout |
| Program owner and PM, Santosh Rasputra | Delivery and quality | Builds, runs the pilot, reports metrics |
| Pilot PMs and TPMs (10) | Time saved, trust | Use Mira, give weekly feedback |
| Project stakeholders (leadership, engineering, clients) | Clear updates | Receive emails drafted by Mira and sent by the PM |
| IT and security | Data handling, keys | Review hosting, keys and data policy |
| Data and privacy lead | Personal data | Reviews prompts and traces for personal data |

# 7. Decision-making

- Sponsor decides scope changes, pilot start and the go, change or stop decision.

- Program owner decides prompt and workflow changes inside the approved scope and reports each change.

- Prompt and model changes need a rerun of T1 to T12 with no new failures before release.

- Escalation: a failure of S2 (an invented fact kept in an answer) pauses the pilot until fixed and re-tested.

- Cadence: a 30-minute review each week during the pilot; a decision log kept in the repository.

# 8. Rollout plan for 10 PMs and TPMs

| Step | When | Action |
| --- | --- | --- |
| 1. Prepare | Before 2 Nov 2026 | Host n8n on a company machine or approved cloud; keys in the credential store; each PM gets the chat link; one-page guide with example requests |
| 2. Train | Week 0 | 30-minute session: what Mira can do, how to read the footer, how to report a wrong answer |
| 3. Pilot | Weeks 1 to 4 | Each PM uses Mira on one live project; weekly survey (time saved, trust, errors); Langfuse review of REVIEW-flagged runs |
| 4. Review | End of week 4 | Check S1 to S6; decide go, change or stop |
| 5. Next | After a go | Add task board connector and a human approval step; widen to more teams |